## README
CQEC ML Decoder — Project Tracking Workbook
For Clark Enge & Pranav Reddy · UCSB Data Science Club Project Showcase
Sheet | Purpose | When to use it
Timeline | Key dates and deliverables at a glance | Check at the start of every work session
Tasks | Full action plan: owner, priority, status, due date, notes | Primary working sheet — update status as you go
Phase 4 Results | Current notebook output vs. expected after re-run | Reference before/after the Phase 4 re-run
Re-run Config | Exact cell-by-cell changes needed in the Phase 4 notebook | When Pranav sits down to re-run the notebook
Slide Placeholders | The 20+ `____` blanks in slides_content.md that need filling | After Phase 4 re-run completes — fill values here, then propagate to .md
Issues & Risks | Known problems with mitigations | Pre-presentation review and judge Q&A prep
Repo | https://github.com/pkarakala/cqec-ml-decoder
Submission | Post to team Slack channel by Tue Apr 28, 11:59 PM
Midpoint | Tue Apr 21, 6:30 PM · TD-W 2600 (mandatory, ≥2 members)

## Timeline
Timeline to Project Showcase
Date | Day | Event | Deliverable | Done
2026-04-17 | Fri | Today — plan in hand | Review this workbook; start Phase 4 re-run | Done
2026-04-18 | Sat | Work day | Phase 4 re-run completes; fill slide blanks; fix Phase 3 overfitting | In progress (poster next)
2026-04-19 | Sun | Work day | Update README with real numbers; regenerate .pptx | Not started
2026-04-20 | Mon | Poster build | Poster v1 drafted; blurb written; dry-run the talk | Not started
2026-04-21 | Tue | Midpoint Showcase 2 · 6:30 PM TD-W 2600 | Present poster; take feedback notes | Not started
2026-04-22 | Wed | Incorporate feedback | Apply changes from midpoint feedback | Not started
2026-04-23 | Thu | Stretch work | Latency analysis for Phase 3 & 4 | Not started
2026-04-24 | Fri | Stretch work | Phase 4 drift-rate robustness sweep | Not started
2026-04-25 | Sat | Polish | Poster v2 final pass | Not started
2026-04-26 | Sun | Polish | Cross-check numbers across README, slides, poster | Not started
2026-04-27 | Mon | Final review | Both partners sign off on submission package | Not started
2026-04-28 | Tue | SUBMISSION DEADLINE · 11:59 PM | Post to Slack: poster link + repo link + blurb | Not started
2026-04-30 | Thu | Finalists announced | Check for finalist notification | Not started
2026-05-05 | Mon | Finalist rehearsal (if selected) | 12-min presentation dry-run | Not started
2026-05-08 | Thu | Project Showcase (if selected) | Full presentation | Not started

## Tasks
Action plan — owners, priorities, status
Update Status column as work progresses. Filter by Owner or Phase for focused views.
Progress: | 6 of 18 done |  | Blockers: | 2 open
# | Phase | Task | Owner | Priority | Status | Due | Notes / details
1 | P4 Fix | Re-run Phase 4 with full params & tuned adaptation | Pranav | Blocker | Done | 2026-04-18 | Cell 8: N_TRAJECTORIES=200, T=1000. Cell 12: adapt_lr=0.005, ema_decay=0.5. Hybrid baseline: supervised_every=20. ~20 min runtime. Single biggest unblocker.
2 | P4 Fix | Decide narrative based on re-run results | Both | Blocker | Done | 2026-04-19 | If hybrid-static gap stays <2pp, pivot framing: lead with pseudo-label collapse (89% → 39%) as the headline, frame hybrid as the obvious mitigation. Don't force a gap that isn't there.
3 | P3 Fix | Address Phase 3 GRU overfitting | Clark | High | Done | 2026-04-19 | val_acc peaks at 86.7% epoch 10, drops to 82.9% by epoch 50. Fix: add early stopping + dropout=0.3, re-report peak. Fallback: prep judge answer 'we report final-epoch for fairness; peak was 86.7%.'
4 | Slides | Fill all ____ blanks in slides_content.md | Clark | High | Done | 2026-04-19 | 20+ placeholders across slides 11, 12, 14. Use new numbers from re-run. See Slide Placeholders sheet for tracker.
5 | Docs | Update README Phase 4 section with real numbers | Pranav | High | Done | 2026-04-19 | Line 175 currently says 'results pending full notebook run.' Replace with 5-way comparison table and temporal degradation summary.
6 | Slides | Regenerate .pptx from updated slides_content.md | Pranav | High | Done | 2026-04-19 | Run `python presentation/build_slides.py`. Open in Google Slides. Verify every Phase 4 figure renders at right size.
7 | Poster | Build poster v1 for Midpoint Showcase | Clark | High | Not started | 2026-04-20 | Hero: phase4_accuracy_over_time.png. Layout: problem framing top-left, 4-phase arc middle, results table + temporal plot right. QR code to repo. Use poster workshop slides from club email.
8 | Submission | Write 3–4 sentence brochure blurb | Pranav | High | Not started | 2026-04-20 | Structure: (1) what continuous QEC is, (2) what you built, (3) headline finding (pseudo-label collapse), (4) why it matters. Clark edits.
9 | Prep | Timed 12–15 min talk run-through | Both | Medium | Not started | 2026-04-20 | Focus on slide 12 (hero). Practice exact wording for 'pseudo-label fails because…' — judges will ask about it.
10 | Event | Attend Midpoint Showcase 2 — 6:30 PM TD-W 2600 | Both | Blocker | Not started | 2026-04-21 | Mandatory ≥2 members. Bring poster. Take feedback notes — apply immediately after.
11 | Poster | Incorporate Midpoint feedback | Clark | High | Not started | 2026-04-22 | Whatever tech dev officers flag. Usually clarity/legibility at poster distance.
12 | Analysis | Detection latency analysis for Phase 3 & 4 | Pranav | Medium | Not started | 2026-04-24 | metrics.py already has latency code. One extra figure: timesteps-until-detection by decoder. Strong for judges asking about real-time feasibility.
13 | Analysis | Phase 4 drift-rate robustness sweep | Clark | Medium | Not started | 2026-04-25 | Adaptive GRU across drift rates [0.1x, 0.5x, 1x, 2x, 5x]. Parallels Phase 2 & 3 robustness figures.
14 | Poster | Final poster v2 — submission version | Both | High | Not started | 2026-04-26 | QR code. Cross-check all numbers match README + slides. Export PDF + high-res PNG.
15 | QA | Cross-check all numbers across README, slides, poster | Pranav | High | Not started | 2026-04-27 | Easy to get out of sync. Single source of truth = notebook outputs.
16 | Submission | Submit to Slack channel before 11:59 PM | Pranav | Blocker | Not started | 2026-04-28 | Post all three: poster link, repo link, blurb. Don't leave this to 11:58.
17 | Finals | Prep interactive demo / animated figure | Pranav | Low | Not started | 2026-05-04 | Only if finalists. Accuracy-vs-time animation with 5 decoder lines is memorable.
18 | Finals | Full presentation dry-run | Both | Low | Not started | 2026-05-05 | At rehearsal event. 12-min tight version.

## Phase 4 Results
Phase 4 results — current run vs. target
Current numbers are from the run with N=60, T=800, adapt_lr=0.001, ema_decay=0.7, supervised_every=50. Fill 'After re-run' columns after re-running with tuned params.
Overall test-set accuracy
Decoder | Current (N=60) | After re-run (N=200) | Δ | Seg 1 (low drift) | Seg 5 (high drift) | Drop (pp)
Threshold | 75.49% | 70% |  | 76% | 60%
Bayesian Filter | 80.3% | 76.5% |  | 90.1% | 65%
Static GRU | 87.47% | 86.1% |  | 89.2% | 76%
Adaptive GRU (pseudo-labels) | 83.3% | 78.4% |  | 45.8% | 26.4%
Adaptive GRU (hybrid, every 20) | 87.67% | 85.7% |  | 88.2% | 73.5%
Supervision frequency sweep (hybrid mode)
Note: current run shows non-monotonic results (Every 500 > Every 200) — that's noise, not signal. Re-run with N=200 should smooth this out.
Every N windows | % supervised | Current accuracy | 0.864
Every 10 | 10% | 86.7% | 84.2%
Every 20 | 5% | 87.33% | 80.7%
Every 50 | 2% | 86.28% | 73.6%
Every 100 | 1% | 85.56% | 80.9%
Every 200 | 0.5% | 81.4% | 58.3%
Every 500 | 0.2% | 85.33%
Key findings to preserve in slides
1. Pseudo-label collapse is the hero finding | Adaptive (pseudo) drops 89.3% → 38.8% across drift. Even if hybrid-vs-static is tight, this alone is a paper-worthy result about distribution shift in self-training.
2. Bayesian has the best early performance but the worst degradation | 92.0% → 62.7% is a 29.3pp drop — textbook assumption failure. Use this to motivate why you need data-driven decoders.
3. Static GRU is surprisingly robust | Only 10.1pp drop across drift. This is good for the model but complicates the 'hybrid beats static' narrative. Acknowledge it; don't hide it.
4. Current supervision sweep has noise | N=200 re-run will smooth this. If it doesn't, report the mean of 3 seeds instead of a single run.

## Re-run Config
Phase 4 notebook re-run — exact changes
Open notebooks/04_phase4_adaptive_decoding.ipynb and apply each change below. Run All. Expect ~20 min on M-series Mac.
# | Cell | Parameter | Current value | Change to
1 | Cell 8 (dataset params) | N_TRAJECTORIES | 60 | 200
2 | Cell 8 (dataset params) | T (trajectory length) | 800 | 1000
3 | Cell 12 (adaptive training) | adapt_lr | 0.001 | 0.005
4 | Cell 12 (adaptive training) | ema_decay | 0.7 | 0.5
5 | Cell 17 (hybrid eval) | supervised_every (baseline) | 50 | 20
6 | Cell 26 (supervision sweep) | supervision_rates | [10, 20, 50, 100, 200, 500] | Keep as-is; N=200 will smooth noise
Post-run verification checklist
✓ | Check
☐ | All 18 cells execute without error
☐ | New figures saved to outputs/figures/ (phase4_accuracy_over_time.png is the hero)
☐ | Hybrid-vs-static gap increased (target: ≥3pp overall, ≥10pp at segment 5)
☐ | Supervision sweep is monotonic (every 10 > every 20 > … > every 500)
☐ | Pseudo-label still collapses in segment 5 (this is the headline result — don't lose it)
☐ | Commit + push notebook with outputs so Clark can pull fresh figures
If hybrid gap still tight after re-run
1. | Try adapt_lr=0.01 (more aggressive online updates)
2. | Try ema_decay=0.3 (even less gradient smoothing)
3. | Widen drift ranges: COLORED_ALPHA_END=0.95, TRANSIENT_AMP_END=1.5
4. | Average over 3 random seeds for cleaner statistics
5. | If still tight: pivot narrative — lead with pseudo-label collapse, not hybrid outperformance

## Slide Placeholders
Slide placeholder tracker — fill after Phase 4 re-run
Every `____` in presentation/slides_content.md. Fill Value column, then search-and-replace in the .md file, then regenerate .pptx.
[5 empty] | Filled: | 22 of 22
Slide | Section | Label | 70.0% | Filled:
11 | Overall comparison table | Threshold accuracy | 76.5%
11 | Overall comparison table | Bayesian Filter accuracy | 86.1%
11 | Overall comparison table | Static GRU accuracy | 78.4%
11 | Overall comparison table | Adaptive (pseudo-labels) accuracy | 85.7%
11 | Overall comparison table | Adaptive (hybrid, every 50) accuracy | 76.0 / 90.1 / 89.2 / 45.8 / 88.2
12 | Temporal segment table | Segment 1 — all 5 decoders | 80.5 / 85.9 / 92.4 / 20.9 / 93.4
12 | Temporal segment table | Segment 2 — all 5 decoders | 75.8 / 75.1 / 90.8 / 12.2 / 89.9
12 | Temporal segment table | Segment 3 — all 5 decoders | 57.6 / 66.1 / 81.8 / 19.7 / 82.6
12 | Temporal segment table | Segment 4 — all 5 decoders | 60.0 / 65.0 / 76.0 / 26.4 / 73.5
12 | Temporal segment table | Segment 5 — all 5 decoders | 13.2 pp
12 | Highlights | Static GRU seg 1→5 drop (pp) | 14.7 pp
12 | Highlights | Hybrid seg 1→5 drop (pp) | -2.5 pp (static edges hybrid; pseudo-label collapses)
12 | Highlights | Gap between hybrid and static at seg 5 | 99.9% (effectively saturated)
13 | Pseudo-label failure | Avg confidence at seg 5 | 26.4%
13 | Pseudo-label failure | Accuracy at seg 5 | 86.4%
14 | Supervision sweep table | Every 10 windows accuracy | 84.2%
14 | Supervision sweep table | Every 20 windows accuracy | 80.7%
14 | Supervision sweep table | Every 50 windows accuracy | 73.6%
14 | Supervision sweep table | Every 100 windows accuracy | 80.9%
14 | Supervision sweep table | Every 200 windows accuracy | 58.3%
14 | Supervision sweep table | Every 500 windows accuracy | 86.1%
14 | Supervision sweep table | Static (no adaptation) accuracy

## Issues & Risks
Known issues, risks, and judge Q&A prep
# | Issue | Severity | Mitigation / answer for judges | Addressed
1 | Hybrid vs static gap is ~0.2pp overall (statistically indistinguishable) | Blocker | Re-run with N=200, tuned adapt_lr/ema_decay. If still tight, pivot narrative to lead with pseudo-label collapse. Don't oversell. | Open
2 | Hybrid degrades MORE than static across temporal segments (17.8pp vs 10.1pp drop) | High | This is the sharpest critique a judge could make. Answer honestly: 'Hybrid trades overall stability for online plasticity; it still dramatically beats pure pseudo-label. Future work: better supervision scheduling.' | Addressed
3 | Phase 3 GRU overfits (val_acc 86.7% → 82.9% over epochs) | High | Fix via early stopping + dropout=0.3 and re-report. Or answer: 'We report final-epoch for fair comparison; peak val was 86.7%.' | Open
4 | Supervision frequency sweep is non-monotonic (every 500 > every 200) | Medium | Clear noise. Re-run with N=200 should smooth it. If not, average 3 seeds. | Addressed
5 | Notebook was run at N=60, T=800 — smaller than recommended N=200, T=1000 | Blocker | Just re-run. ~20 min on M-series. This is the single unblocker. | Addressed
6 | README still says 'results pending full notebook run' (line 175) | Medium | Update after re-run. Bad look if a judge clones the repo and sees this. | Open
7 | Phase 4 notebook cell 16 shows stale predict_adaptive signature (no supervised_every param) | Low | Cosmetic — re-running the notebook will fix it. If not, delete that cell. | Open
8 | Bayesian filter only tested from Phase 2 onwards (not Phase 1) | Low | Not a real problem — Bayesian is optimal under Phase 1 assumptions by construction. Answer: 'Phase 1 is the sanity check; Bayesian is the theoretical optimum there.' | Open
9 | Only 3-qubit repetition code, not a real surface code | Low | Listed as future work in README. Answer: 'The code is representative; the decoder architecture generalizes. Surface code extension is future work.' | Open
10 | No comparison to published ML decoder work (Chamberland, Varbanov, etc.) | Low | Honest answer: 'This is an undergraduate project focused on the analog/continuous setting; prior ML decoder work is mostly on discrete syndromes. Direct comparison is future work.' | Open